## Project Plan
Task | PIC | Status | Date / Due Date | Notes
Day 1: Project Setup & Data Aggregation Layer
Set up Python environment and install dependencies (FastAPI, feedparser, requests, python-dotenv). | Dzikri Rabbani | Belum Berjalan | 25 Sep 2026
Setup local PostgreSQL database with `pgvector` extension. | Dzikri Rabbani | Belum Berjalan | 25 Sep 2026
Create the data aggregation script to parse RSS feeds from financial news outlets. | Dzikri Rabbani | Belum Berjalan | 25 Sep 2026
Integrate secondary APIs (GNews/NewsAPI) as fallbacks. | Dzikri Rabbani | Belum Berjalan | 25 Sep 2026
Implement basic data normalization and deduplication to avoid redundant news. | Dzikri Rabbani | Belum Berjalan | 25 Sep 2026
Day 2: Topic Clustering, Trend Scoring, & Database Integration
Implement `SentenceTransformers` for local text embedding to save API costs. | Dzikri Rabbani | Belum Berjalan | 26 Sep 2026
Build the Topic Clustering module using similarity search in `pgvector`. | Dzikri Rabbani | Belum Berjalan | 26 Sep 2026
Develop a scoring algorithm based on freshness, volume, and relevance. | Dzikri Rabbani | Belum Berjalan | 26 Sep 2026
Filter the top 5 highest-scoring topics per day. | Dzikri Rabbani | Belum Berjalan | 26 Sep 2026
Save normalized topics, sources, and claims into the database. | Dzikri Rabbani | Belum Berjalan | 26 Sep 2026
Day 3: AI Research & Article Generation Pipeline
Establish connection to Gemini API. | Dzikri Rabbani | Belum Berjalan | 27 Sep 2026
Build the **Evidence Store** logic: extract solid facts and figures from the selected top topics. | Dzikri Rabbani | Belum Berjalan | 27 Sep 2026
Design the strict AI Prompts/Templates for the article structure (Headline, Lead, Body with financial data, Insight). | Dzikri Rabbani | Belum Berjalan | 27 Sep 2026
Ensure prompt instructions strictly forbid hallucinations and plagiarism, enforcing an evidence-based approach. | Dzikri Rabbani | Belum Berjalan | 27 Sep 2026
Implement language logic (English) with formal/journalistic tone tailored for C-level executives. | Dzikri Rabbani | Belum Berjalan | 27 Sep 2026
Day 4: Fact-Checking, Compliance & SEO Optimization
Build the **Automated Fact-Checking** module to cross-reference AI-generated numbers/claims against the Evidence Store. | Dzikri Rabbani | Belum Berjalan | 28 Sep 2026
Implement a fallback mechanism: if fact-check fails, discard the article and optionally retry. | Dzikri Rabbani | Belum Berjalan | 28 Sep 2026
Inject mandatory legal disclaimers ("Not financial advice") and source attributions. | Dzikri Rabbani | Belum Berjalan | 28 Sep 2026
Implement the SEO Optimization module: generate meta titles, descriptions, and structure HTML/Markdown headings. | Dzikri Rabbani | Belum Berjalan | 28 Sep 2026
Day 5: Orchestration (n8n) & CMS Integration
Set up **n8n** (or alternative orchestrator) workflows to trigger tasks. | Dzikri Rabbani | Belum Berjalan | 29 Sep 2026
Create the daily schedule logic (e.g., Data collection at 01:00, generation at 05:00, final validation at 07:00). | Dzikri Rabbani | Belum Berjalan | 29 Sep 2026
Enforce the **Hard-Limit**: strictly maximum 5 articles per day, max 1 per topic category. | Dzikri Rabbani | Belum Berjalan | 29 Sep 2026
Integrate with WordPress REST API (or Headless CMS) to push generated articles. | Dzikri Rabbani | Belum Berjalan | 29 Sep 2026
Implement logic to hold "Ready" articles in a *Scheduled/Draft* state until the 08:00 WIB auto-publish window. | Dzikri Rabbani | Belum Berjalan | 29 Sep 2026
Day 6: Admin Dashboard (Streamlit MVP) & Testing
Build a simple **Streamlit Dashboard** to view daily quotas, generation status, and logs. | Dzikri Rabbani | Belum Berjalan | 30 Sep 2026
Implement toggle controls: *Auto Schedule Mode* vs *Manual Selection Mode*. | Dzikri Rabbani | Belum Berjalan | 30 Sep 2026
Allow admin to manually select topics and force-generate articles (within the 5/day limit). | Dzikri Rabbani | Belum Berjalan | 30 Sep 2026
End-to-end testing of the pipeline (simulate a full day's run). | Dzikri Rabbani | Belum Berjalan | 30 Sep 2026
Setup error tracking and hallucination logs for future prompt iterations. | Dzikri Rabbani | Belum Berjalan | 30 Sep 2026