## Project Plan
Task | PIC | Status | Date / Due Date | Notes
Phase 1: Foundation & Database Blueprint (Days 1-2)
Define the Tech Stack (e.g., Next.js for Frontend, Node.js/Python for Backend, PostgreSQL for DB). | Dzikri Rabbani | Belum Berjalan | 03 Oct 2026 - 04 Oct 2026
Design the Database Schema (ERD): | Dzikri Rabbani | Belum Berjalan | 03 Oct 2026 - 04 Oct 2026
- `users`, `roles` | Dzikri Rabbani | Belum Berjalan | 03 Oct 2026 - 04 Oct 2026
- `products`, `categories` | Dzikri Rabbani | Belum Berjalan | 03 Oct 2026 - 04 Oct 2026
- `orders`, `order_items`, `payments` | Dzikri Rabbani | Belum Berjalan | 03 Oct 2026 - 04 Oct 2026
- `entitlements` (User Library Access) | Dzikri Rabbani | Belum Berjalan | 03 Oct 2026 - 04 Oct 2026
Setup repository and base project structure for Backend and Frontend. | Dzikri Rabbani | Belum Berjalan | 03 Oct 2026 - 04 Oct 2026
Phase 2: Core Backend & Authentication (Days 3-5)
Implement User Authentication (Register, Login, JWT). | Dzikri Rabbani | Belum Berjalan | 05 Oct 2026 - 07 Oct 2026
Build Admin Auth & Role Validation. | Dzikri Rabbani | Belum Berjalan | 05 Oct 2026 - 07 Oct 2026
Create CRUD APIs for **Categories** and **Products** (Supporting different Product Types: Ebook, Journal, Article, File). | Dzikri Rabbani | Belum Berjalan | 05 Oct 2026 - 07 Oct 2026
Implement secure file upload for digital assets (storing them in protected cloud storage/directories, NOT public folders). | Dzikri Rabbani | Belum Berjalan | 05 Oct 2026 - 07 Oct 2026
Phase 3: Admin Dashboard Development (Days 6-8)
Build the Admin UI layout (Sidebar, Header, Overview). | Dzikri Rabbani | Belum Berjalan | 08 Oct 2026 - 10 Oct 2026
Implement Product Management (Create, Edit, Upload Cover, Upload Digital Asset). | Dzikri Rabbani | Belum Berjalan | 08 Oct 2026 - 10 Oct 2026
Implement Category Management. | Dzikri Rabbani | Belum Berjalan | 08 Oct 2026 - 10 Oct 2026
Order & Customer Management (View transactions and statuses). | Dzikri Rabbani | Belum Berjalan | 08 Oct 2026 - 10 Oct 2026
Phase 4: Customer Frontend - Discovery & Cart (Days 9-11)
Build the Public Website layout (Landing Page, Navbar, Footer). | Dzikri Rabbani | Belum Berjalan | 11 Oct 2026 - 13 Oct 2026
Implement Product Catalog, Search, and Category Filtering. | Dzikri Rabbani | Belum Berjalan | 11 Oct 2026 - 13 Oct 2026
Build Product Detail Page (Displaying price, description, and preview). | Dzikri Rabbani | Belum Berjalan | 11 Oct 2026 - 13 Oct 2026
Implement Shopping Cart (Add, Remove, Subtotal calculation). | Dzikri Rabbani | Belum Berjalan | 11 Oct 2026 - 13 Oct 2026
Phase 5: Checkout & Payment Gateway Integration (Days 12-14)
Implement the Checkout flow (Order Summary). | Dzikri Rabbani | Belum Berjalan | 14 Oct 2026 - 16 Oct 2026
Integrate a Payment Gateway (e.g., Midtrans, Xendit, or Stripe). | Dzikri Rabbani | Belum Berjalan | 14 Oct 2026 - 16 Oct 2026
Handle **Webhook Integration** to securely verify successful payments. | Dzikri Rabbani | Belum Berjalan | 14 Oct 2026 - 16 Oct 2026
Automate Order Status updates (Pending -> Paid -> Failed). | Dzikri Rabbani | Belum Berjalan | 14 Oct 2026 - 16 Oct 2026
Phase 6: User Library & Digital Entitlement (Days 15-17)
Logic to generate `entitlements` when an order status becomes PAID. | Dzikri Rabbani | Belum Berjalan | 17 Oct 2026 - 19 Oct 2026
Build the **"My Library"** section on the customer frontend. | Dzikri Rabbani | Belum Berjalan | 17 Oct 2026 - 19 Oct 2026
Implement Secure Access Control: generate temporary signed URLs or stream files based on the user's entitlement and the Product Type. | Dzikri Rabbani | Belum Berjalan | 17 Oct 2026 - 19 Oct 2026
Build basic readers (e.g., PDF Reader or simple Article view) for the web. | Dzikri Rabbani | Belum Berjalan | 17 Oct 2026 - 19 Oct 2026
Phase 7: Testing, Security & Deployment (Days 18-20)
End-to-end flow testing (Registration -> Browse -> Buy -> Pay -> Read). | Dzikri Rabbani | Belum Berjalan | 20 Oct 2026 - 22 Oct 2026
Security audit: prevent direct file access, validate inputs, check JWT scopes. | Dzikri Rabbani | Belum Berjalan | 20 Oct 2026 - 22 Oct 2026
Set up production databases and storage buckets. | Dzikri Rabbani | Belum Berjalan | 20 Oct 2026 - 22 Oct 2026
Deploy Backend and Frontend to cloud platforms (e.g., Vercel, AWS, or DigitalOcean). | Dzikri Rabbani | Belum Berjalan | 20 Oct 2026 - 22 Oct 2026
Configure domain and SSL. | Dzikri Rabbani | Belum Berjalan | 20 Oct 2026 - 22 Oct 2026